## Template
Feature Specification
Project Name: | Reviewed By:
Feature Code: | Review Date:
Feature Name: | Estimated Time (Hrs):
Feature URL: | Sprint:
Assignee: | Start Date:
Status: | Due Date:
Percent Progress: | Spent Time (Hrs):
User Story:
Specifications:
Additional Note:

## Sprints
Sprints | Features Code | Feature Name | Assignee | Start Date | End Date
Sprint 1
| CC01 | Home Page - Student (Front End) | Fernandez, Leah | 2023-09-15 | 2023-09-22
| CC02 | Login (Front-End) | Amadeo, Carl | 2023-09-15 | 2023-09-22
| CC03-S | Signup-Student (Front End) | Ando, Roger | 2023-09-15 | 2023-09-22
| CC03-T | Signup-Teacher (Front-End) | Ando, Roger | 2023-09-15 | 2023-09-22
| CC04 | Landing Page (Front End) | Rotor, Jhames Paul | 2023-09-15 | 2023-09-22
| CC05 | Home Page - Teacher (Front End) | Ontal, Ryan | 2023-09-15 | 2023-09-22
Sprint 2
| CC06 | Login-Signup(Back-end) | Amadeo, Carl
| CC07 | Forgot Password | Fernandez, Leah
| CC08 | View Profile -Student and Teacher (Front End) | Ando, Roger
| CC09 | View Courses - Teacher | Ontal, Ryan
| CC10 | Contacts (Back End) | Rotor, Jhames Paul
| CC11 | Add course ( Teacher) | Ontal, Ryan
Sprint 3
Enroll course (Student)
Progress Tracking (Student)
View topics (Student)
Course List (Student)
Add course (Student)
Sprint 4
Certificate
Sprint 5
Sprint 6

## CC01
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ontal, Ryan Christian R.
Feature Code: | CC01 | Review Date: | 2023-09-24
Feature Name: | Home Page - Student (Front-End) | Estimated Time (Hrs): | 30
Feature URL: | http://localhost:3000/studenthomepage | Sprint: | Sprint 1
Assignee: | Fernandez, Ma. Leahlyn | Start Date: | 2023-09-15
Status: | Done | Due Date: | 2023-09-24
Percent Progress: | 100% | Spent Time (Hrs): | 15
User Story: | • As a student user, I want to visit the homepage of the app so that I can easily discover and access courses and certifications that interest me. • As a student user, I want a search bar that is visible near the top of the page, allowing me to search for specific courses or topics of interest. • As a student user, it is better that there should be a prominent link or button for accessing support or FAQs, in case I have questions or need assistance. And a SignOut button for easy navigation when I want to sign out.
Specifications: | This will display the following: • Navigation Menu (Options: My Courses, Certifications, My Profile, SignOut) • Implement Search Bar for Courses on top of the page • Include a "Support" link in the navigation menu, leading to a dedicated support page.
Additional Note:

## CC02
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ontal, Ryan Chrisitan
Feature Code: | CC02 | Review Date: | 2023-09-24
Feature Name: | Login - Front End | Estimated Time (Hrs): | 72
Feature URL: | http://localhost:3000/#login | Sprint: | Sprint 1
Assignee: | Carl Marlo M. Amadeo | Start Date: | 2023-09-16
Status: | Done | Due Date: | 2023-09-22
Percent Progress: | 100% | Spent Time (Hrs): | 23
User Story: | • As a user, I want to choose to log in as a student or teacher. • As a student user, I want to login so that I can access the student's dashboard. • As a teacher user, I want to login so that I can access the teacher's dashboard.
Specifications: | This will display the following : • Input field for "Email" • Input field for "Password" • "Forgot Password" link for password reset • "View Password" eye icon for password view • Smooth transition to the student's home page upon successful login • Smooth transition to the teacher's home page upon successful login • User-friendly design and responsive layout for various devices • HREF for "Student" this will redirect to student signup • HREF for "Teacher" this will redirect to teacher signup
Additional Note:

## CC03-T
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ontal, Ryan
Feature Code: | CC03 | Review Date: | 2023-09-24
Feature Name: | Sign Up - Teacher (Front-End) | Estimated Time (Hrs): | 20
Feature URL: | http://localhost:3000/teachersignup | Sprint: | Sprint 1
Assignee: | Roger R. Ando | Start Date: | 2023-09-13
Status: | Done | Due Date: | 2023-09-22
Percent Progress: | 100% | Spent Time (Hrs): | 13
User Story: | • As a teacher user, I want to create an account. • As a user, I want to login.
Specifications: | This will display the following: • Input field for "First Name" • Input field for "Last Name" • Input field for "Email" • Input field for "Password" • Input field for "Confirm Password" • Input field for "Link of all credentials" • Button for "Sign Up" - After filling all the required input you will redirect to login page in order to login your newly created account. • Select field for "Date of Birth" • Select field for "Gender" • Link (Href) for "Login"
Additional Note: | The user should input all the required input field to create an account.

## CC03-S
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ontal, Ryan
Feature Code: | CC03 | Review Date: | 2023-09-24
Feature Name: | Sign Up - Student (Front-End) | Estimated Time (Hrs): | 20
Feature URL: | http://localhost:3000/studentsignup | Sprint: | Sprint 1
Assignee: | Roger R. Ando | Start Date: | 2023-09-13
Status: | Done | Due Date: | 2023-09-22
Percent Progress: | 100% | Spent Time (Hrs): | 13
User Story: | • As a student user, I want to create an account. • As a user, I want to login.
Specifications: | This will display the following: • Input field for "First Name" • Input field for "Last Name" • Input field for "Email" • Input field for "Password" • Input field for "Confirm Password" • Button for "Sign Up" - After filling all the required input you will redirect to login page in order to login your newly created account. • Select field for "Date of Birth" • Select field for "Gender" • Link (Href) for "Login"
Additional Note: | The user should input all the required input field to create an account.

## CC04
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ontal, Ryan Christian
Feature Code: | CC04 | Review Date: | 2023-09-24
Feature Name: | Landing Page - Front End | Estimated Time (Hrs): | 72
Feature URL: | http://localhost:3000 | Sprint: | Sprint 1
Assignee: | Rotor, Jhames Paul | Start Date: | 2023-09-15
Status: | Done | Due Date: | 2023-09-22
Percent Progress: | 100% | Spent Time (Hrs): | 72
User Story: | •As a user, I want to see a headline that is appealing and clear, letting me know right away what the website is about. •As a user, I want to navigate more information about the website. •As a user, I want to know the contact details of the important person who runs this website so I may get in touch with them and ask more questions. •As a user, I want to know more about the services that the product can offer to us. •As a user, I need to login the website in order for me to access the home page.
Specifications: | This page will display the following fields: •Button for "About" •Button for ''Services" •Button for "Contact" •Button for "Log in" •Exhibits Headlines
Additional Note:

## CC05
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ando, Roger
Feature Code: | CC05 | Review Date: | 2023-09-24
Feature Name: | Home Page - Teacher (Front End) | Estimated Time (Hrs): | 48
Feature URL: | http://localhost:3000/teacherhomepage | Sprint: | Sprint 1
Assignee: | Ontal, Ryan Christian | Start Date: | 2023-09-15
Status: | Done | Due Date: | 2023-09-22
Percent Progress: | 100% | Spent Time (Hrs): | 10
User Story: | • As a teacher user, I want to add courses. • As a teacher user, I want to view the courses that I am handling. • As a teacher user, I want to view my profile.
Specifications: | This will display the following: • Button for add course • Button for View Profile • Button for View Course • Input field for "Search Course" • Button for Signout
Additional Note: