## Template
Feature Specification
Project Name: | Reviewed By:
Feature Code: | Review Date:
Feature Name: | Estimated Time (Hrs):
Feature URL: | Sprint:
Assignee: | Start Date:
Status: | Due Date:
Percent Progress: | Spent Time (Hrs):
User Story:
Specifications:
Additional Note:

## Sprints
Sprints | Features Code | Feature Name | Assignee | Start Date | End Date
Sprint 1
| CC01 | Home Page - Student (Front End) | Fernandez, Leah | 2023-09-15 | 2023-09-22
| CC02 | Login (Front-End) | Amadeo, Carl | 2023-09-15 | 2023-09-22
| CC03-S | Signup-Student (Front End) | Ando, Roger | 2023-09-15 | 2023-09-22
| CC03-T | Signup-Teacher (Front-End) | Ando, Roger | 2023-09-15 | 2023-09-22
| CC04 | Landing Page (Front End) | Rotor, Jhames Paul | 2023-09-15 | 2023-09-22
| CC05 | Home Page - Teacher (Front End) | Ontal, Ryan | 2023-09-15 | 2023-09-22
Sprint 2
| CC06 | Login-Signup(Back-end) | Amadeo, Carl | 2023-10-02 | 2023-10-06
| CC07 | Add Topic (Teacher) - Front End | Fernandez, Leah | 2023-10-02 | 2023-10-08
| CC08-T | View Profile -Student (Front End) | Ando, Roger | 2023-09-27 | 2023-10-08
| CC08-S | View Profile - Teacher (Front End) | Ando, Roger | 2023-09-27 | 2023-10-08
| CC09 | View Courses - Teacher | Ontal, Ryan | 2023-09-27 | 2023-10-08
| CC10-00 | MoreDetails (Landing Page) | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-01 | About | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-02 | Services | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-03 | Contact | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC11 | Add course - Teacher | Ontal, Ryan | 2023-09-27 | 2023-10-08
Sprint 3
Enroll course (Student)
View Profile Student - BackEnd
View Profile Teacher - BackEnd
Add Topics Teacher - BackEnd
View Course (Student)
Forgot Password
Sprint 4
Quiz
Search Bar - Teacher
Search Bar - Student
Profile - Teacher
Profile - Student
Sprint 5
Sprint 6

## CC06
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC06 | Review Date: | 2023-10-09
Feature Name: | Login-Signup(Back-end) | Estimated Time (Hrs): | 45
Feature URL: | http://localhost:3000/loginsignup | Sprint: | Sprint 2
Assignee: | Amadeo, Carl Marlo | Start Date: | 2023-10-02
Status: | Done | Due Date: | 2023-10-06
Percent Progress: | 100% | Spent Time (Hrs): | 48
User Story: | • As a user, I want to be able to securely log in to the CourCert platform and, if I don't have an account, sign up for a new account.
Specifications: | Login: • Authentication - Query the database to find a user with the provided username or email. • Response - Return an appropriate response indicating success or failure. Signup: • Duplicate Check - Check if the provided username and email are not already in use. • User Creation - If email is unique, create a new user account in the database. • Response - Return an appropriate response indicating success or failure. Error Handling: • Invalid Credentials - If login fails, provide a clear error message indicating whether it's due to invalid email or password. • Duplicate Account - If signup fails due to duplicate username or email, provide a clear error message.
Additional Note:

## CC07
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC07 | Review Date: | 2023-10-09
Feature Name: | Add Topic (Teacher)- Front End | Estimated Time (Hrs): | 60
Feature URL: | http://localhost:3000/teacheraddcourse | Sprint: | Sprint 2
Assignee: | Ma. Leahlyn G. Fernandez | Start Date: | 2023-10-02
Status: | Done | Due Date: | 2023-10-08
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | • As a teacher user, I want to add topics that is related to the course.
Specifications: | This feature would allow user the following: • Attach a file • Name of the file uploaded • Edit Course Description • Edit Course Title • Edit week number This will display the following: • Button for "View course" • Button "back" for List of Courses (View Course) • Button for "Account Profile" • Button for "Add New Tile"
Additional Note:

## CC08-T
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC08-S | Review Date: | 2023-10-09
Feature Name: | Profile Account - Teacher(frontend) | Estimated Time (Hrs): | 35
Feature URL: | http://localhost:3000/teacherprofile | Sprint: | Sprint 2
Assignee: | Roger R. Ando | Start Date: | 2023-09-27
Status: | Done | Due Date: | 2023-10-08
Percent Progress: | 100% | Spent Time (Hrs): | 18
User Story: | • As a teacher user, I want to see my personal details.
Specifications: | This will display the following: • Text field for "First Name" • Text field for "Last Name" • Text field for "Email" • Text field for "Birth date" • Image for profile picture • Button for "Update Profile" • Button for "Back"
Additional Note:

## CC08-S
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC08-S | Review Date: | 2023-10-09
Feature Name: | Profile Account - Student(frontend) | Estimated Time (Hrs): | 35
Feature URL: | http://localhost:3000/profilepage | Sprint: | Sprint 2
Assignee: | Roger R. Ando | Start Date: | 2023-09-27
Status: | Done | Due Date: | 2023-10-08
Percent Progress: | 100% | Spent Time (Hrs): | 18
User Story: | • As a student user, I want to view my profile.
Specifications: | This will display the following: • Text field for "First Name" • Text field for "Last Name" • Text field for "Email" • Text field for "Birth date" • Image for profile picture • Button for "Update profile" • Button for "Back"
Additional Note:

## CC09
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Carl Amadeo
Feature Code: | CC09 | Review Date: | 2023-10-09
Feature Name: | View Courses - Teacher | Estimated Time (Hrs): | 72
Feature URL: |  | Sprint: | Sprint 2
Assignee: | Ontal, Ryan Christian | Start Date: | 2023-09-27
Status: | Done | Due Date: | 2023-10-08
Percent Progress: | 100% | Spent Time (Hrs): | 56
User Story: | • As a teacher user, I want to view the courses I'm handling.
Specifications: | This will display the following: • List of Courses • Button for Add Course • Button for View Profile • Button for View Course • Input field for "Search Course" • Button for Signout
Additional Note:

## CC10.00
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC10-00 | Review Date: | 2023-10-09
Feature Name: | More Details (Landing Page) | Estimated Time (Hrs): | 72
Feature URL: | http://localhost:3000/MoreDetails | Sprint: | Sprint 2
Assignee: | Rotor, Jhames Paul | Start Date: | 2023-09-29
Status: | Done | Due Date: | 2023-10-08
Percent Progress: | 100% | Spent Time (Hrs): | 72
User Story: | •As a user, I want to know more about cour-cert.
Specifications: | This page will display the following: •The illustration of the advantages of Cour-cert. •The description of every illustration.
Additional Note:

## CC10.01
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC10-01 | Review Date: | 2023-10-09
Feature Name: | About Page | Estimated Time (Hrs): | 72
Feature URL: | http://localhost:3000/about | Sprint: | Sprint 2
Assignee: | Rotor, Jhames Paul | Start Date: | 2023-09-29
Status: | Done | Due Date: | 2023-10-08
Percent Progress: | 100% | Spent Time (Hrs): | 72
User Story: | •As a user, I would want additional information about the website.
Specifications: | This page will display the following: •The website's overview. •Button for Learn More. -proceed to another page •Our Mission •Our Vision
Additional Note:

## CC10.02
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC10-02 | Review Date: | 10/09//2023
Feature Name: | Services Page | Estimated Time (Hrs): | 72
Feature URL: | http://localhost:3000/services | Sprint: | Sprint 2
Assignee: | Rotor, Jhames Paul | Start Date: | 2023-09-29
Status: | Done | Due Date: | 2023-10-08
Percent Progress: | 100% | Spent Time (Hrs): | 72
User Story: | •As a user, I would want to know what services the website provides.
Specifications: | This page will display the following: •A summary of our services •"Content Delivery" •"Interactive Learning Tools" •"Progress Tracking"
Additional Note:

## CC10.03
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC10-03 | Review Date: | 2023-10-09
Feature Name: | Contact Page | Estimated Time (Hrs): | 72
Feature URL: | http://localhost:3000/contact | Sprint: | Sprint 2
Assignee: | Rotor, Jhames Paul | Start Date: | 2023-09-29
Status: | Done | Due Date: | 2023-10-08
Percent Progress: | 100% | Spent Time (Hrs): | 72
User Story: | •As a user, I want to contact the developer of the website for certain clarifications or questions.
Specifications: | This page will display the following: •input field "user_email" •Submit Button •Warning notification if the field is not inputted •A message indicating whether or not the email is valid •A notification will appear specifying the submitting of an email.
Additional Note:

## CC11
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Carl Amadeo
Feature Code: | CC11 | Review Date: | 2023-10-09
Feature Name: | Add Course | Estimated Time (Hrs): | 48
Feature URL: | http://localhost:3000/teacherhomepage | Sprint: | Sprint 1
Assignee: | Ontal, Ryan Christian | Start Date: | 2023-09-27
Status: | Done | Due Date: | 2023-10-08
Percent Progress: | 100% | Spent Time (Hrs): | 29
User Story: | • As a teacher user, I want to add courses.
Specifications: | This will pop a dialogue box with input fields: • Input field for "Course Name" • Input field for 'Course Description" Redirect to new page and will display the following: • Course name • Button for View Profile • Button for View Course • Input field for "Search Course" • Button for Add topics • Button for Signout
Additional Note: