## Template
Feature Specification
Project Name: | Reviewed By:
Feature Code: | Review Date:
Feature Name: | Estimated Time (Hrs):
Feature URL: | Sprint:
Assignee: | Start Date:
Status: | Due Date:
Percent Progress: | Spent Time (Hrs):
User Story:
Specifications:
Additional Note:

## Sprints
Sprints | Features Code | Feature Name | Assignee | Start Date | End Date
Sprint 1
| CC01 | Home Page - Student (Front End) | Fernandez, Leah | 2023-09-15 | 2023-09-22
| CC02 | Login (Front-End) | Amadeo, Carl | 2023-09-15 | 2023-09-22
| CC03-S | Signup-Student (Front End) | Ando, Roger | 2023-09-15 | 2023-09-22
| CC03-T | Signup-Teacher (Front-End) | Ando, Roger | 2023-09-15 | 2023-09-22
| CC04 | Landing Page (Front End) | Rotor, Jhames Paul | 2023-09-15 | 2023-09-22
| CC05 | Home Page - Teacher (Front End) | Ontal, Ryan | 2023-09-15 | 2023-09-22
Sprint 2
| CC06 | Login-Signup(Back-end) | Amadeo, Carl | 2023-10-02 | 2023-10-06
| CC07 | Add Topic (Teacher) - Front End | Fernandez, Leah | 2023-10-02 | 2023-10-08
| CC08-T | View Profile -Student (Front End) | Ando, Roger | 2023-09-27 | 2023-10-08
| CC08-S | View Profile - Teacher (Front End) | Ando, Roger | 2023-09-27 | 2023-10-08
| CC09 | View Courses - Teacher | Ontal, Ryan | 2023-09-27 | 2023-10-08
| CC10-00 | MoreDetails (Landing Page) | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-01 | About | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-02 | Services | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-03 | Contact | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC11 | Add course - Teacher | Ontal, Ryan | 2023-09-27 | 2023-10-08
Sprint 3
| CC12 | All Course List - Student | Ando, Roger | 2023-10-16
| CC13 | View Course Page (Student) (Front End) | Ando, Roger | 16/13/2023
| CC14 | Show/Edit Profile Student - BackEnd | Fernandez, Leah | 2023-10-24
| CC15 | Show/Edit Profile Teacher - BackEnd | Fernandez, Leah | 2023-10-24
| CC16 | Add Topics Teacher - BackEnd | Ontal, Ryan
| CC17 | Forgot Password | Amadeo, Carl | 2023-10-16 | 2023-10-18
| CC18 | Reset Password | Amadeo, Carl | 2023-10-16 | 2023-10-20
| CC19-001 | Login Page (Admin) | Rotor, Jhames Paul | 2023-10-24
| CC19-002 | Sign Up Page (Admin) | Rotor, Jhames Paul | 2023-10-24
Sprint 4
Quiz
Search Bar - Teacher
Search Bar - Student
Profile - Teacher
Profile - Student
Sprint 5
Sprint 6

## CC12
Feature Specification
Project Name: | Cour-Cert | Reviewed By:
Feature Code: | CC12 | Review Date:
Feature Name: | All Course List - Student | Estimated Time (Hrs): | 18
Feature URL: | http://localhost:3000/allcourselist | Sprint: | Sprint 3
Assignee: | Ando, Roger R. | Start Date: | 2023-10-16
Status: | In-progress | Due Date:
Percent Progress: | 80% | Spent Time (Hrs):
User Story: | • As a user, I want to enroll this course. • As a user, I want to go back to homepage. • As a user, I want to check the Course Outline.
Specifications: | This will display the following: • Search Bar • Button for "My Course" • Button for "Back" • Button for "Enroll Course" • Href for "Title" • Img that has href to go back to the homepage.
Additional Note:

## CC13
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC07 | Review Date: | 2023-10-09
Feature Name: | Add Topic (Teacher)- Front End | Estimated Time (Hrs): | 60
Feature URL: | http://localhost:3000/teacheraddcourse | Sprint: | Sprint 2
Assignee: | Ma. Leahlyn G. Fernandez | Start Date: | 2023-10-02
Status: | Done | Due Date: | 2023-10-08
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | • As a teacher user, I want to add topics that is related to the course.
Specifications: | This feature would allow user the following: • Attach a file • Name of the file uploaded • Edit Course Description • Edit Course Title • Edit week number This will display the following: • Button for "View course" • Button "back" for List of Courses (View Course) • Button for "Account Profile" • Button for "Add New Tile"
Additional Note:

## CC14
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC14 | Review Date: | 2023-10-09
Feature Name: | Show/Edit Profile Details Student - BackEnd | Estimated Time (Hrs): | 35
Feature URL: | http://localhost:3000/profilepage | Sprint: | Sprint 3
Assignee: | Ma. Leahlyn Fernandez | Start Date: | 2023-10-24
Status: | In-progress | Due Date:
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | • As a student user, I want to see and edit the details on my profile.
Specifications: | This will display the following user details: • First Name • Last Name • Email This will have the following functionality: • Edit text field for "First Name" • Edit text field for "Last Name" • Text field for "Email"
Additional Note:

## CC15
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC15 | Review Date:
Feature Name: | Show/Edit Profile Details Teacher - BackEnd | Estimated Time (Hrs): | 35
Feature URL: | http://localhost:3000/teacherprofile | Sprint: | Sprint 3
Assignee: | Ma. Leahlyn G. Fernandez | Start Date: | 2023-10-24
Status: | In-progress | Due Date:
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | • As a teacher user, I want to see and edit my personal details.
Specifications: | "This will display the following user details: • First Name • Last Name • Email This will have the following functionality: • Edit text field for ""First Name"" • Edit text field for ""Last Name"" • Text field for ""Email"
Additional Note:

## CC16
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Carl Amadeo
Feature Code: | CC16 | Review Date: | 2023-10-09
Feature Name: | Add Topics - Teacher (BackEnd) | Estimated Time (Hrs): | 72
Feature URL: |  | Sprint: | Sprint 3
Assignee: | Ontal, Ryan Christian | Start Date: | 2023-09-27
Status: | Done | Due Date: | 2023-10-08
Percent Progress: | 50% | Spent Time (Hrs): | 56
User Story: | • As a teacher user, I want to edit the course title, course description • As a teacher user, I want to add week number, upload PDF file and PDF Title • As a teacher user, I want to add new week
Specifications: | This will display the following: • Button for View Profile • Button for View Course • Input field for Course Title • Input field for Course Description • Input field for Week • Input field for PDF Title • Button for Save Changes • Button for Add New Week • Button for Back
Additional Note:

## CC17
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC17 | Review Date: | 2023-10-25
Feature Name: | Forgot Password | Estimated Time (Hrs): | 72
Feature URL: | http://localhost:3000/forgotpassword | Sprint: | Sprint 3
Assignee: | Amadeo, Carl | Start Date: | 2023-10-16
Status: | Done | Due Date: | 2023-10-22
Percent Progress: | 100% | Spent Time (Hrs): | 43
User Story: | •As a registered user of CourCert, I want to be able to reset my password in case I forget it, So that I can regain access to my account without creating a new one.
Specifications: | This will display the following: •The Forgot Password Page •The Email Text Box •"Send Password Reset Link" Button •"Cancel" Button •Password Reset Link •Success Prompt •Error Prompt
Additional Note:

## CC18
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC18 | Review Date: | 2023-10-25
Feature Name: | Reset Password | Estimated Time (Hrs): | 48
Feature URL: | http://localhost:3000/resetpassword/ | Sprint: | Sprint 3
Assignee: | Amadeo, Carl Marlo | Start Date: | 2023-10-16
Status: | Done | Due Date: | 2023-10-22
Percent Progress: | 100% | Spent Time (Hrs): | 16
User Story: | •As a user who has initiated a password reset, I want to be able to set a new password for my account, So that I can regain access with a secure and updated password.
Specifications: | This will display the following: •The Reset Password Page •"New Password" Text Box •"Confirm New Password" Text Box •"Password Eye View" Button •"Set New Password" Button •"Security Password Tips" Text •Success Prompt •Error Prompt
Additional Note:

## CC19-001
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC19-001 | Review Date: | 10/27//2023
Feature Name: | Login Page (Admin) | Estimated Time (Hrs): | 72
Feature URL: | http://localhost:3000/Admin | Sprint: | Sprint 3
Assignee: | Rotor, Jhames Paul | Start Date: | 2023-10-24
Status: | Done | Due Date: | 2023-10-27
Percent Progress: | 80% | Spent Time (Hrs): | 72
User Story: | •As an authorized user, I would want to login as an admin of the website.
Specifications: | This page will display the following: •Input Field for "Email" •Input Field for "password" •Checkbox of "Remember me" •Link "Forgot Password" - Direct towards the forgot password page then the system will ask the user for the secret key inorder to verify if the user is a legitimate admin then proceed into executing to changing password. •Login Button - Direct towards Admin Home Page •"Login Succesful" - Message indicating a successful log in •Link "Sign Up" - Direct to Sign Up page
_
Additional Note:

## CC19-002
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC19-002 | Review Date: | 10/27//2023
Feature Name: | Sign Up Page (Admin) | Estimated Time (Hrs): | 72
Feature URL: | http://localhost:3001/Admin/sign-up | Sprint: | Sprint 3
Assignee: | Rotor, Jhames Paul | Start Date: | 2023-10-24
Status: | Done | Due Date: | 2023-10-27
Percent Progress: | 80% | Spent Time (Hrs): | 72
User Story: | •As an authorized user, I would want to register as an admin of the website.
Specifications: | This page will display the following: •Input Field for "Secret Key" •Input Field for "Firstname" •Input Field for "Lastname" •Input Field for "Email" •Input Field for "password" •"Sign Up" Button - Submit all credentials •"Invalid Admin" - Serves as a warning message indicating that the user has inputted the wrong Secret Key •"Registration Successful" - Notifies the user of successful registration •Link "Log in" - Go back to Log in page
_
Additional Note: