## Template
Feature Specification
Project Name: | Reviewed By:
Feature Code: | Review Date:
Feature Name: | Estimated Time (Hrs):
Feature URL: | Sprint:
Assignee: | Start Date:
Status: | Due Date:
Percent Progress: | Spent Time (Hrs):
User Story:
Specifications:
Additional Note:

## Sprints
Sprints | Features Code | Feature Name | Assignee | Start Date | End Date
Sprint 1
| CC01 | Home Page - Student (Front End) | Fernandez, Leah | 2023-09-15 | 2023-09-22
| CC02 | Login (Front-End) | Amadeo, Carl | 2023-09-15 | 2023-09-22
| CC03-S | Signup-Student (Front End) | Ando, Roger | 2023-09-15 | 2023-09-22
| CC03-T | Signup-Teacher (Front-End) | Ando, Roger | 2023-09-15 | 2023-09-22
| CC04 | Landing Page (Front End) | Rotor, Jhames Paul | 2023-09-15 | 2023-09-22
| CC05 | Home Page - Teacher (Front End) | Ontal, Ryan | 2023-09-15 | 2023-09-22
Sprint 2
| CC06 | Login-Signup(Back-end) | Amadeo, Carl | 2023-10-02 | 2023-10-06
| CC07 | Add Topic (Teacher) - Front End | Fernandez, Leah | 2023-10-02 | 2023-10-08
| CC08-T | View Profile -Student (Front End) | Ando, Roger | 2023-09-27 | 2023-10-08
| CC08-S | View Profile - Teacher (Front End) | Ando, Roger | 2023-09-27 | 2023-10-08
| CC09 | View Courses - Teacher | Ontal, Ryan | 2023-09-27 | 2023-10-08
| CC10-00 | MoreDetails (Landing Page) | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-01 | About | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-02 | Services | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-03 | Contact | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC11 | Add course - Teacher | Ontal, Ryan | 2023-09-27 | 2023-10-08
Sprint 3
| CC12 | All Course List - Student | Ando, Roger | 2023-10-16
| CC13 | View Course Page (Student) (Front End) | Ando, Roger | 16/13/2023
| CC14 | Show/Edit Profile Student - BackEnd | Fernandez, Leah | 2023-10-24
| CC15 | Show/Edit Profile Teacher - BackEnd | Fernandez, Leah | 2023-10-24
| CC16 | Add Topics Teacher - BackEnd | Ontal, Ryan | 2023-10-24
| CC17 | Forgot Password | Amadeo, Carl | 2023-10-16 | 2023-10-18
| CC18 | Reset Password | Amadeo, Carl | 2023-10-16 | 2023-10-20
| CC19-001 | Login Page (Admin) | Rotor, Jhames Paul | 2023-10-24
| CC19-002 | Sign Up Page (Admin) | Rotor, Jhames Paul | 2023-10-24
Sprint 4
| CC20 | Search Bar - Teacher (Backend) | Fernandez, Leah | 2023-11-16 | 2023-11-17
| CC21 | Search Bar - Student (Backend) | Fernandez, Leah | 2023-11-13 | 2023-11-17
| CC22 | Update Profile Details (Backend) - Teacher | Fernandez, Leah | 2023-11-10 | 2023-11-12
| CC23 | Update Profile Details (Backend) - Student | Fernandez, Leah | 2023-11-11 | 2023-11-13
| CC24 | Authentication | Amadeo, Carl | 2023-11-02 | 2023-11-17
| CC25 | Enroll Course | Ando, Roger | 2023-11-12 | 2023-11-17
| CC26 | My Course | Ando, Roger | 2023-11-12 | 2023-11-16
| CC27 | Forgot Password (Admin) | Rotor, Jhames Paul | 2023-11-15
Sprint 5
Sprint 6

## CC20
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC20 | Review Date: | 2023-10-09
Feature Name: | Search Bar - Teacher (Backend) | Estimated Time (Hrs): | 60
Feature URL: | http://localhost:3000/teacherhomepage | Sprint: | Sprint 4
Assignee: | Ma. Leahlyn G. Fernandez | Start Date: | 2023-10-16
Status: | In-progress | Due Date: | 2023-10-17
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | • As a teacher user, I want to search courses in the search bar button in the homepage.
Specifications: | This will have the following functionality: • Can type in the search bar button for courses • Display search results for the courses
Additional Note:

## CC21
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC21 | Review Date: | 2023-11-17
Feature Name: | Search Bar - Student (Backend) | Estimated Time (Hrs): | 35
Feature URL: | http://localhost:3000/studenthomepage | Sprint: | Sprint 4
Assignee: | Ma. Leahlyn Fernandez | Start Date: | 2023-11-13
Status: | In-progress | Due Date: | 2023-11-17
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | • As a student user, I want to search courses in the search bar button in the homepage.
Specifications: | This will have the following functionality: • Can type in the search bar button for courses • Display search results for the courses
Additional Note:

## CC22
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC22 | Review Date: | 2023-11-17
Feature Name: | Update Profile Details (Backend) - Teacher | Estimated Time (Hrs): | 35
Feature URL: | http://localhost:3000/teacherprofile | Sprint: | Sprint 4
Assignee: | Ma. Leahlyn G. Fernandez | Start Date: | 2023-11-10
Status: | Done | Due Date: | 2023-11-17
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | • As a teacher user, I want to update my profile details as I want.
Specifications: | This will have the following functionality: • When "Update" button is clicked, the details of the user has been updated in the database. • A success message will pop up for a successful update of the user details.
Additional Note: | Together in this sprint (in Teacher Profile end), a button for change password (with dropdown) is added.

## CC23
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Carl Amadeo
Feature Code: | CC23 | Review Date: | 2023-11-17
Feature Name: | Update Profile Details (Backend) - Student | Estimated Time (Hrs): | 35
Feature URL: | http://localhost:3000/profilepage | Sprint: | Sprint 4
Assignee: | Ma. Leahlyn G. Fernandez | Start Date: | 2023-11-10
Status: | Done | Due Date: | 2023-11-17
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | • As a teacher user, I want to update my profile details as I want.
Specifications: | This will have the following functionality: • When "Update" button is clicked, the details of the user has been updated in the database. • A success message will pop up for a successful update of the user details.
Additional Note: | Together in this sprint (in Teacher Profile end), a button for change password (with dropdown) is added.

## CC24
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ontal, Ryan
Feature Code: | CC24 | Review Date: | 2023-11-17
Feature Name: | Authentication | Estimated Time (Hrs): | 72
Feature URL: | http://localhost:3000/loginsignup | Sprint: | Sprint 4
Assignee: | Amadeo, Carl | Start Date: | 2023-11-07
Status: | Done | Due Date: | 2023-11-13
Percent Progress: | 100% | Spent Time (Hrs): | 78
User Story: | •As a user, I want to securely log in to CourCert using my credentials, and upon successful authentication, I should be granted access to the website's homepage, profile, and other features. Unauthorized access attempts or tampering with URL links without proper authentication should be prevented.
Specifications: | This feature applies the following: • JWT Authorization
Additional Note:

## CC25
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian Ontal
Feature Code: | CC25 | Review Date: | 2023-11-17
Feature Name: | Enroll Course | Estimated Time (Hrs): | 56
Feature URL: | http://localhost:3000/allcourselist | Sprint: | Sprint 4
Assignee: | Ando, Roger R. | Start Date: | 2023-11-07
Status: | Done | Due Date: | 2023-11-13
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | •As a user, I wan to see my enroll a course.
Specifications: | This will have the following functionality: • Button for "Enroll Course" • Button for "My Course"
Additional Note:

## CC26
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian R Ontal
Feature Code: | CC26 | Review Date: | 2023-11-17
Feature Name: | Student View Course | Estimated Time (Hrs): | 56
Feature URL: | http://localhost:3000/loginsignup | Sprint: | Sprint 4
Assignee: | Ando, Roger R. | Start Date: | 2023-11-07
Status: | In-progress | Due Date: | 2023-11-13
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | •As a user, I want to see my enrolled courses.
Specifications: | This will have the following functionality: • Button for "Back" • Button for "Account Profile" • Button "View My Course" • Button for "Available Courses" • Link for "Title" to redirect "courseviewpage"
Additional Note:

## CC27
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Christian R. Ontal
Feature Code: | CC27 | Review Date: | 2023-11-17
Feature Name: | Forgot Password (Admin) | Estimated Time (Hrs): | 72
Feature URL: | http://localhost:3001/Admin/ForgotPassword | Sprint: | Sprint 4
Assignee: | Rotor, Jhames Paul S. | Start Date: | 2023-11-14
Status: | In-progress | Due Date: | 2023-11-20
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | •As an authorized admin user, I want to reset and change my password by the time I forgot my password for my account.
Specifications: | This feature will display the following: • Input field for "user_email" •Submit button - once the user click submit. Our system will send email to the user for the link of Reset Password •Alert Message "Submitted, please check your email" - once the proper email has been entered, and click the submit button. The user will receive a notification to move on to the next phase by clicking the link on their email for password reset. •Alert Message "User not Exists!" - if the user inputted the wrong email. The system will send an alert message indicating that the email is not recognized in the database. •Cancel button - this will go to the admin login page •Link for Reset Password •Input Field for "new_password" (For Reset Password) •Input Field for "confirm_password" (For Reset Password) •Submit button - after clicking the button, the password has been changed and the user can proceed to the login page admin •Alert Message "Do you want to login?" - the user can click ok button once the message appears on the screen then it will redirect to the admin login page
Additional Note: