## Template
Feature Specification
Project Name: | Reviewed By:
Feature Code: | Review Date:
Feature Name: | Estimated Time (Hrs):
Feature URL: | Sprint:
Assignee: | Start Date:
Status: | Due Date:
Percent Progress: | Spent Time (Hrs):
User Story:
Specifications:
Additional Note:

## Sprints
Sprints | Features Code | Feature Name | Assignee | Start Date | End Date
Sprint 1
| CC01 | Home Page - Student (Front End) | Fernandez, Leah | 2023-09-15 | 2023-09-22
| CC02 | Login (Front-End) | Amadeo, Carl | 2023-09-15 | 2023-09-22
| CC03-S | Signup-Student (Front End) | Ando, Roger | 2023-09-15 | 2023-09-22
| CC03-T | Signup-Teacher (Front-End) | Ando, Roger | 2023-09-15 | 2023-09-22
| CC04 | Landing Page (Front End) | Rotor, Jhames Paul | 2023-09-15 | 2023-09-22
| CC05 | Home Page - Teacher (Front End) | Ontal, Ryan | 2023-09-15 | 2023-09-22
Sprint 2
| CC06 | Login-Signup(Back-end) | Amadeo, Carl | 2023-10-02 | 2023-10-06
| CC07 | Add Topic (Teacher) - Front End | Fernandez, Leah | 2023-10-02 | 2023-10-08
| CC08-T | View Profile -Student (Front End) | Ando, Roger | 2023-09-27 | 2023-10-08
| CC08-S | View Profile - Teacher (Front End) | Ando, Roger | 2023-09-27 | 2023-10-08
| CC09 | View Courses - Teacher | Ontal, Ryan | 2023-09-27 | 2023-10-08
| CC10-00 | MoreDetails (Landing Page) | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-01 | About | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-02 | Services | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-03 | Contact | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC11 | Add course - Teacher | Ontal, Ryan | 2023-09-27 | 2023-10-08
Sprint 3
| CC12 | All Course List - Student | Ando, Roger | 2023-10-16
| CC13 | View Course Page (Student) (Front End) | Ando, Roger | 16/13/2023
| CC14 | Show/Edit Profile Student - BackEnd | Fernandez, Leah | 2023-10-24
| CC15 | Show/Edit Profile Teacher - BackEnd | Fernandez, Leah | 2023-10-24
| CC16 | Add Topics Teacher - BackEnd | Ontal, Ryan | 2023-10-24
| CC17 | Forgot Password | Amadeo, Carl | 2023-10-16 | 2023-10-18
| CC18 | Reset Password | Amadeo, Carl | 2023-10-16 | 2023-10-20
| CC19-001 | Login Page (Admin) | Rotor, Jhames Paul | 2023-10-24
| CC19-002 | Sign Up Page (Admin) | Rotor, Jhames Paul | 2023-10-24
Sprint 4
| CC20 | Search Bar - Teacher (Backend) | Fernandez, Leah | 2023-11-16 | 2023-11-17
| CC21 | Search Bar - Student (Backend) | Fernandez, Leah | 2023-11-13 | 2023-11-17
| CC22 | Update Profile Details (Backend) - Teacher | Fernandez, Leah | 2023-11-10 | 2023-11-12
| CC23 | Update Profile Details (Backend) - Student | Fernandez, Leah | 2023-11-11 | 2023-11-13
| CC24 | Authentication | Amadeo, Carl | 2023-11-02 | 2023-11-17
| CC25 | Enroll Course | Ando, Roger | 2023-11-12 | 2023-11-17
| CC26 | My Course | Ando, Roger | 2023-11-12 | 2023-11-16
| CC27 | Forgot Password (Admin) | Rotor, Jhames Paul | 2023-11-15
Sprint 5
| CC28 | Upload Profile Picture - Student | Ontal, Ryan | 2023-11-27 | 2023-11-30
| CC29 | Upload Profile Picture - Teacher | Ontal, Ryan | 2023-11-27 | 2023-11-30
| CC30 | Course View Topics - Student (BackEnd) | Ontal, Ryan | 2023-11-20 | 2023-11-27
| CC31 | Show List of Students & Delete - Admin (Frontend & Backend) | Fernandez, Leah | 2023-11-29 | 2023-12-01
| CC32 | Show List of Teachers & Delete - Admin (Frontend & Backend) | Fernandez, Leah | 2023-11-30 | 2023-12-02
| CC33 | Questionnaire - Student Side | Amadeo, Carl | 2023-11-15 | 2023-12-01
| CC34 | Questionnaire - Teacher Add Quiz | Amadeo, Carl | 2023-11-24 | 2023-12-02
Sprint 6

## CC28
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Amadeo, Carl
Feature Code: | CC28 | Review Date: | 2023-11-30
Feature Name: | Upload Profile Picture - Student (BackEnd) | Estimated Time (Hrs): | 60
Feature URL: | http://localhost:3000/teacherhomepage | Sprint: | Sprint 5
Assignee: | Ontal, Ryan Christian R. | Start Date: | 2023-11-27
Status: | Done | Due Date: | 2023-11-30
Percent Progress: | 100% | Spent Time (Hrs): | 24
User Story: | • As a student user, I want to upload my own profile picture.
Specifications: | This will have the following functionality: • "Edit" button to enable users edit first name, last name • "Change Password" button to enable users edit password • "Upload image" button to enable users to upload profile picture • "Update" button to enable users to save changes that has been made • "Cancel" button to enable users to cancel changes that has been made • "Back" button to enable users to redirect to the homepage |  |  | 0
Additional Note:

## CC29
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Amadeo, Carl
Feature Code: | CC21 | Review Date: | 2023-11-30
Feature Name: | Upload Profile Picture - Teacher (BackEnd) | Estimated Time (Hrs): | 35
Feature URL: | http://localhost:3000/studenthomepage | Sprint: | Sprint 5
Assignee: | Ontal, Ryan Christian | Start Date: | 2023-11-27
Status: | Done | Due Date: | 2023-11-30
Percent Progress: | 100% | Spent Time (Hrs): | 24
User Story: | • As a teacher user, I want to upload my profile picture.
Specifications: | This will have the following functionality: • "Edit" button to enable users edit first name, last name • "Change Password" button to enable users edit password • "Upload image" button to enable users to upload profile picture • "Update" button to enable users to save changes that has been made • "Cancel" button to enable users to cancel changes that has been made • "Back" button to enable users to redirect to the homepage
Additional Note:

## CC30
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Amadeo, Carl
Feature Code: | CC30 | Review Date: | 2023-11-30
Feature Name: | Course View Topics - Student (BackEnd) | Estimated Time (Hrs): | 35
Feature URL: | http://localhost:3000/teacherprofile | Sprint: | Sprint 5
Assignee: | Ontal, Ryan Christian | Start Date: | 2023-11-20
Status: | Done | Due Date: | 2023-11-27
Percent Progress: | 100% | Spent Time (Hrs): | 30
User Story: | • As a student, I want to see or know what are the topics in this course.
Specifications: | This will have the following functionality: • "View Course" button to redirect user to his/her Courses that are available. • "Back" button to redirect user to his/her Courses that are available. • "Topic Description" button to redirect user to the content of the topic. • Weekly Topics button to redirect user to his/her Courses that are available.
Additional Note:

## CC31
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ryan Ontal
Feature Code: | CC31 | Review Date: | 2023-12-01
Feature Name: | Show List of Students & Delete - Admin (Frontend & Backend) | Estimated Time (Hrs): | 35
Feature URL: | http://localhost:3000/Admin/ListOfStudents | Sprint: | Sprint 4
Assignee: | Ma. Leahlyn G. Fernandez | Start Date: | 2023-11-29
Status: | Done | Due Date: | 2023-12-01
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | • As a an admin, I want to see the list of students and can delete their data in just a click.
Specifications: | This will display the following: • List of Students that are registered in the database • Delete Button beside the Name of the Students Users This will have the following functionality: • Dsiplay all the user students that are stored in the database. • When "Delete" button is clicked, the user data in the database will be deleted.
Additional Note:

## CC32
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ontal, Ryan
Feature Code: | CC32 | Review Date: | 2023-12-01
Feature Name: | Show List of Teachers & Delete - Admin (Frontend & Backend) | Estimated Time (Hrs): | 35
Feature URL: | http://localhost:3000/Admin/ListOfTeachers | Sprint: | Sprint 5
Assignee: | Ma. Leahlyn G. Fernandez | Start Date: | 2023-11-29
Status: | In-progress | Due Date: | 2023-12-01
Percent Progress: | 80% | Spent Time (Hrs):
User Story: | • As a an admin, I want to see the list of teachers and can delete their data in just a click.
Specifications: | This will display the following: • List of Teachers that are registered in the database • Delete Button beside the Name of the Teachers Users This will have the following functionality: • Display all the user teachers that are stored in the database. • When "Delete" button is clicked, the user data in the database will be deleted.
Additional Note:

## CC33
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ontal, Ryan
Feature Code: | CC35 | Review Date: | 2023-12-02
Feature Name: | Questionnaire - Student Side | Estimated Time (Hrs): | 72
Feature URL: | http://localhost:3000/courseviewpage | Sprint: | Sprint 5
Assignee: | Amadeo, Carl | Start Date: | 2023-11-15
Status: | Done | Due Date: | 2023-12-02
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | • As a student user, I want to be able to assess my learnings by answering quizzes that are tailored to the courses I have applied for. This feature will enhance my understanding of the course materials and help me gauge my progress.
Specifications: | This feature will display the following: • Questions • Radio Button for choices • Submit Button • Retake Button "If user cant get perfect answer" • Message label for score.
Additional Note:

## CC34
Feature Specification
Project Name: | Cour-Cert | Reviewed By: | Ontal, Ryan
Feature Code: | CC36 | Review Date: | 2023-12-04
Feature Name: | Questionnaire - Teacher Add Quiz | Estimated Time (Hrs): | 72
Feature URL: | http://localhost:3000/teacheraddcourse | Sprint: | Sprint 5
Assignee: | Amadeo, Carl | Start Date: | 2023-11-24
Status: | In-progress | Due Date: | 2023-12-02
Percent Progress: | 100% | Spent Time (Hrs):
User Story: | • As a teacher user, I want to be able to create quizzes within the courses I have designed for my students. This will allow me to assess their understanding of the material and track their progress effectively.
Specifications: | This feature will display the following: • textBox for Questions • textBox for choices • textBox for correct answer • button for Add Question • button for Add Quiz
Additional Note: