## Template
Feature Specification
Project Name: | Reviewed By:
Feature Code: | Review Date:
Feature Name: | Estimated Time (Hrs):
Feature URL: | Sprint:
Assignee: | Start Date:
Status: | Due Date:
Percent Progress: | Spent Time (Hrs):
User Story:
Specifications:
Additional Note:

## Sprints
Sprints | Features Code | Feature Name | Assignee | Start Date | End Date
Sprint 1
| CC01 | Home Page - Student (Front End) | Fernandez, Leah | 2023-09-15 | 2023-09-22
| CC02 | Login (Front-End) | Amadeo, Carl | 2023-09-15 | 2023-09-22
| CC03-S | Signup-Student (Front End) | Ando, Roger | 2023-09-15 | 2023-09-22
| CC03-T | Signup-Teacher (Front-End) | Ando, Roger | 2023-09-15 | 2023-09-22
| CC04 | Landing Page (Front End) | Rotor, Jhames Paul | 2023-09-15 | 2023-09-22
| CC05 | Home Page - Teacher (Front End) | Ontal, Ryan | 2023-09-15 | 2023-09-22
Sprint 2
| CC06 | Login-Signup(Back-end) | Amadeo, Carl | 2023-10-02 | 2023-10-06
| CC07 | Add Topic (Teacher) - Front End | Fernandez, Leah | 2023-10-02 | 2023-10-08
| CC08-T | View Profile -Student (Front End) | Ando, Roger | 2023-09-27 | 2023-10-08
| CC08-S | View Profile - Teacher (Front End) | Ando, Roger | 2023-09-27 | 2023-10-08
| CC09 | View Courses - Teacher | Ontal, Ryan | 2023-09-27 | 2023-10-08
| CC10-00 | MoreDetails (Landing Page) | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-01 | About | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-02 | Services | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC10-03 | Contact | Rotor, Jhames Paul | 2023-09-29 | 2023-10-08
| CC11 | Add course - Teacher | Ontal, Ryan | 2023-09-27 | 2023-10-08
Sprint 3
| CC12 | All Course List - Student | Ando, Roger | 2023-10-16
| CC13 | View Course Page (Student) (Front End) | Ando, Roger | 16/13/2023
| CC14 | Show/Edit Profile Student - BackEnd | Fernandez, Leah | 2023-10-24
| CC15 | Show/Edit Profile Teacher - BackEnd | Fernandez, Leah | 2023-10-24
| CC16 | Add Topics Teacher - BackEnd | Ontal, Ryan | 2023-10-24
| CC17 | Forgot Password | Amadeo, Carl | 2023-10-16 | 2023-10-18
| CC18 | Reset Password | Amadeo, Carl | 2023-10-16 | 2023-10-20
| CC19-001 | Login Page (Admin) | Rotor, Jhames Paul | 2023-10-24
| CC19-002 | Sign Up Page (Admin) | Rotor, Jhames Paul | 2023-10-24
Sprint 4
| CC20 | Search Bar - Teacher (Backend) | Fernandez, Leah | 2023-11-16 | 2023-11-17
| CC21 | Search Bar - Student (Backend) | Fernandez, Leah | 2023-11-13 | 2023-11-17
| CC22 | Update Profile Details (Backend) - Teacher | Fernandez, Leah | 2023-11-10 | 2023-11-12
| CC23 | Update Profile Details (Backend) - Student | Fernandez, Leah | 2023-11-11 | 2023-11-13
| CC24 | Authentication | Amadeo, Carl | 2023-11-02 | 2023-11-17
| CC25 | Enroll Course | Ando, Roger | 2023-11-12 | 2023-11-17
| CC26 | My Course | Ando, Roger | 2023-11-12 | 2023-11-16
| CC27 | Forgot Password (Admin) | Rotor, Jhames Paul | 2023-11-15
Sprint 5
| CC28 | Upload Profile Picture - Student | Ontal, Ryan | 2023-11-27 | 2023-11-30
| CC29 | Upload Profile Picture - Teacher | Ontal, Ryan | 2023-11-27 | 2023-11-30
| CC30 | Course View Topics - Student (BackEnd) | Ontal, Ryan | 2023-11-20 | 2023-11-27
| CC31 | Show List of Students & Delete - Admin (Frontend & Backend) | Fernandez, Leah | 2023-11-29 | 2023-12-01
| CC32 | Show List of Teachers & Delete - Admin (Frontend & Backend) | Fernandez, Leah | 2023-11-30 | 2023-12-02
| CC35 | Questionnaire - Student Side | Amadeo, Carl | 2023-11-15 | 2023-12-01
| CC36 | Questionnaire - Teacher Add Quiz | Amadeo, Carl | 2023-11-24 | 2023-12-02
Sprint 6
| CC37 | Profile Reset Password | Amadeo, Carl | 2023-12-07 | 2023-12-09
| CC38 | Password Hashing | Amadeo, Carl | 2023-12-05 | 2023-12-10

## CC37
Feature Specification
Project Name: | Cour-Cert | Reviewed By:
Feature Code: | CC37 | Review Date:
Feature Name: | Profile Reset Password | Estimated Time (Hrs): | 12
Feature URL: | http://localhost:3000/profilepage | Sprint: | Sprint 5
Assignee: | Amadeo, Carl | Start Date: | 2023-12-07
Status: | Done | Due Date: | 2023-12-09
Percent Progress: | 100% | Spent Time (Hrs): | 8
User Story: | • As a registered user of Cour-Cert, I want the ability to reset my password from my profile, so that I can secure my account in case I want to change my current password.
Specifications: | This will have the following functionality: • TextBox for "Password" • TextBox for "Confirm Password" • Button for "Update Password" • Error Label "Password do not match." • Success Label "Password changed successfully."
Additional Note:

## CC38
Feature Specification
Project Name: | Cour-Cert | Reviewed By:
Feature Code: | CC38 | Review Date:
Feature Name: | Password Hashing | Estimated Time (Hrs): | 26
Feature URL: | http://localhost:3000/loginsignup | Sprint: | Sprint 5
Assignee: | Amadeo, Carl | Start Date: | 2023-12-05
Status: | Done | Due Date: | 2023-12-10
Percent Progress: | 100% | Spent Time (Hrs): | 14
User Story: | • As a security-conscious developer of Cour-Cert, I want to implement password hashing for user accounts to ensure that sensitive information is stored securely.
Specifications: | This will apply the following functionality: • Implement Hashing • Enforce password complexity rules (e.g., minimum length, uppercase/lowercase letters, numbers, special characters).
Additional Note: